## Secondments (new)
| ID | Profile | Sending Organization | Seconded to Organi-zation | Work package no | Second-ment Starting Month | Duration of Secondment (Researcher- Months)
ER, ESR, TECH, MNG or ADM
ILTSR-1 | 1 | ER | ILTSR | FSGSU |  | 3 | 1 | ER | Researcher | FSGSU | 1 | 10 | 1 |  | CANCELED, moved to YG
ILTSR-1 | WS | ER | ILTSR | SPMRC | 3 | 21 | 1 | ESR | Early Stage Researcher | [5 empty] | CANCELED, moved to YG, RT, KL
ILTSR-1 |  | ER | ILTSR | FSGSU | 7 | 48 | 1 | MNG | Management
ILTSR-2 | 2 | ER | ILTSR | SPMRC | 2 | 4 | 1 | [7 empty] | DONE
ILTSR-2 | AŁ | ER | ILTSR | SPMRC | 5 | 29 | 1
ILTSR-2 |  | ER | ILTSR | FSGSU | 7 | 42 | 1
ILTSR-3 | 3 | ER | ILTSR | FSGSU | 2 | 8 | 1 |  |  | 2 | 9 | 1 |  |  | DONE
ILTSR-3 | DH | ER | ILTSR | FSGSU | 7 | 42 | 1
ILTSR-4 | 4 | ESR | ILTSR | SPMRC | 1 | 4 | 1 |  | DONE | SPMRC | 3 | 22 | 1/3 | add | DONE
ILTSR-4 | RT | ESR | ILTSR | FSGSU | 5 | 39 | 1
ILTSR-4 |  | ESR | ILTSR | FSGSU | 7 | 30 | 1
ILTSR-5 | 5 | ESR | ILTSR | SPMRC | 1 | 4 | 1 |  | DONE | SPMRC | 3 | 23 | 1/3 | add | DONE
ILTSR-5 | KL | ESR | ILTSR | FSGSU | 7 | 30 | 1
ILTSR-6 | 6 | ESR | ILTSR | SPMRC | 1 | 32 | 1
ILTSR-6 | AW | ESR | ILTSR | SPMRC | 5 | 18 | 1 |  |  |  |  | 23 |  |  | DONE
ILTSR-6 |  | ESR | ILTSR | FSGSU | 7 | 41 | 1 | 19
ILTSR-7 | 7 | ER | ILTSR | SPMRC | 1 | 1 | 1 | DONE |  | FSGSU | 1 | 10 | 1 | add | DONE | instead of WS
ILTSR-7 | YG | ER | ILTSR | FSGSU | 1 | 13 | 1 | DONE |  | SPMRC | 3 | 24 | 1/3 | add | DONE
ILTSR-7 |  | ER | ILTSR | FSGSU | 1 | 27 | 1 | DONE
VU-1 | 8 | ER | VU | Nanocer | 7 | 9 | 1 | [7 empty] | CANCELED
VU-1 | AK | ER | VU | SPRMC | 1 | 26 | 1
VU-2 | 9 | ER | VU | SPRMC | 1 | 4 | 2 |  |  | SPRMC | 1 | 5 | 1 |  | DONE
VU-2 | IGP | ER | VU | FSGSU | 1 | 36 | 1 |  |  | SPMRC | 2 | 24 | 1 | added | moved to #newAZ
VU-2 |  | ER | VU | Nanocer | 6 | 46 | 1 |  |  | FSGSU | 1 | 25 | 1 | added | DONE
VU-3 | 10 | ESR | VU | SPRMC | 1 | 16 & 17 | 2 |  | moved to JR & APa | SPRMC | 1 | 8 -> 10 | 1 | added | DONE
VU-3 | DK | ESR | VU | FSGSU | 2 | 25 | 1 |  | moved to AZ
VU-4 | 11 | ESR | VU | Nanocer | 6 | 9 | 2 |  |  | NC | 1 | 9 | 1 |  | DONE
VU-4 | OO | ESR | VU | FSGSU | 1 | 35 | 1
VU-5 | 12 | ESR | VU | Nanocer | 6 | 32 & 33 | 2 | 16 |  | NC | 7 | 8 | 1 | added | DONE
VU-5 | RS | ER | VU | SPMRC | 2 | 24 | 1 |  | moved to IGP
VU-6 | new-AZ | ESR | VU | SPMRC | 2 | 24 | 1 | added | DONE | FSGSU | 2 | 25 | 1 | added | moved to #9
VU-7 | new-Apo | ESR | VU
VU-8 | newMS/JR | ESR | VU | [6 empty] | SPRMC | 1 | 17 | 1 | added | DONE
VU-9 | new-APa | ESR | VU | [6 empty] | SPMRC | 1 | 17 | 1 | added | DONE
VU-10 | new-ZS | ER | VU | [6 empty] | NC | 1 | 8 | 1 |  | DONE
FSGSU-1 | 13 | ER | FSGSU | ILTSR | 2 | 6 | 2 | [7 empty] | DONE
FSGSU-1 | VG | ER | FSGSU | ILTSR | 2 | 19 | 2 |  | M20 moved to #14 M19 |  |  |  | 1 |  | DONE
FSGSU-1 |  | ER | FSGSU | ILTSR | 2 | 31 | 2 |  |  |  |  | 25/28&37 |  | started
FSGSU-1 |  | ER | FSGSU | Nanocer | 7 | 44 | 1 |  |  | UA | 5 | 32&34 | 1 | 1m added
FSGSU-1 |  | ER | FSGSU | HZG | 2 | 4 | 1 |  | moved to MM in July | HZG | 2 | 16 | 1
[10 empty] | VU | 3 | 33 | 1 | added
FSGSU-2 | 14 | ER | FSGSU | VU | 1 | 11 | 2 | [7 empty] | DONE
FSGSU-2 | DK | ER | FSGSU | ILTSR | 1 | 6 | 1 | [7 empty] | DONE
FSGSU-2 |  | ER | FSGSU | Nanocer | 6 | 44 | 1 |  |  | ILTSR | 2 | 19 | 1 | added | not rep | DONE
FSGSU-2 |  | ER | FSGSU | HZG | 2 | 28 | 2 |  | #17 M29 & #19 M29 | UA | 5 | 20 | 1 | added | not rep
[10 empty] | ILTSR | 3 | 37 | 1 | added
FSGSU-3 | 15 | ER | FSGSU | VU | 1 | 9 | 2 |  |  | VU | 1 | 11 | 2 |  | DONE
FSGSU-3 | AS | ER | FSGSU | ILTSR | 1 | 21 | 1 |  |  | ILTSR | 1 | 6 (i21) | 1 |  | DONE
FSGSU-3 |  | ER | FSGSU | HZG | 2 | 28 | 2 |  | 1m moved to #16 M32 |  |  | 30 | 1
[10 empty] | NC | 6 | 28 | 1 | added
FSGSU-4 | 16 | ER | FSGSU | VU | 3 | 26 | 1 |  | moved to #13 M33 | HZG | 2 | 20 | 1 | added from VG |  | Reported | DONE
FSGSU-4 | MM | ER | FSGSU | ILTSR | 3 | 34 | 1 |  | moved to #14 M37 | HZG | 2 | 32 | 1 | added
FSGSU-5 | 17 | ESR | FSGSU | VU | 3 | 26 | 1 |  | moved to #18 M33 | HZG | 2 | 29 | 1 | added
FSGSU-5 | YK | ESR | FSGSU | ILTSR | 3 | 34 | 1 |  | moved to #18 M37
FSGSU-5 | ER ? | ESR | FSGSU | HZG | 2 | 17 | 1 |  |  |  | 2 | 20 | 1 |  |  | Reported | DONE
FSGSU-6 | 18 | ESR | FSGSU | VU | 3 | 24 | 1 |  |  |  |  | 21 |  |  | not rep | DONE
FSGSU-6 | SK | ESR | FSGSU | UA | 5 | 18 | 1 |  | M20 moved to #13 M20 | ILTSR | 1 | 24 | 1 | added | not rep | DONE
FSGSU-6 |  | ESR | FSGSU | Nanocer | 6 | 30 | 1 |  | moved to #15 M28 | VU | 3 | 33 | 1 | added
[10 empty] | ILTSR | 1 | 37 | 1 | added
FSGSU-7 | 19 | ESR | FSGSU | ILTSR | 1 | 18 | 1 | 30 | M20 moved to #18 M24 | HZG | 2 | 29 | 1 | added
| VS | ESR | FSGSU | UA | 5 | 28 | 1 |  | moved to #13 M34
FSGSU-7 |  | ESR | FSGSU | IoP | 4 | 20 | 1 | [7 empty] | DONE
UA-1 | 20 | MNG | UA | Nanocer | 3 | 9 | 1 |  | DONE |  | 6 | 28 | 1 | added
UA-1 | AK | MNG | UA | SPRMC | 7 | 47 | 1 |  | ? to be updated |  | 1 | 28 | 1 | added
UA-2 | 21 | ESR | UA | SPRMC | 1 | 15 | 2 |  | 1m moved to #24 |  | 1 | 19 23 | 1 | Reported/not rep |  | DONE
UA-2 | PZ | ESR->ER | UA | SPRMC | 1 | 30 | 1 |  |  |  | 1 | 29 | 1 | added
UA-3 | 22 | DA-ER | UA | SPRMC | 1 | 15 | 2 |  |  |  | 1 | 17 | 2 | two-month shift - not reported |  |  |  | DONE
UA-4 | 23 | ER | UA | SPRMC | 1 | 25 | 2 |  |  |  |  | 28&30
UA-4 | SK | ER | UA | FSGSU | 1 | 36 | 2 | 13 | 1m moved to #21 |  |  | ?? | 1
UA-5 | 24 | Xx-ESR | UA | Nanocer | 6 | 18 | 2 |  | 1m moved to #20 |  | 6 | >26 | 2
UA-5 | VS |  | UA | [5 empty] | Vladislav Slabov | SPMRC | 1 | 21 | 1 | added | DONE
IoP-1 | 25 | ER | IoP | Nanocer | 7 | 9 | 1 |  | moved to AY, M17
IoP-1 |  | ER | IoP | SPRMC | 4 | 19 | 1 |  | ??
IoP-1 |  | ER | IoP | FSGSU | 3 | 30 | 1
IoP-2 | 26 | ER | IoP | Nanocer | 6 | 9 | 1 |  |  |  | 6 | 17 |  | DONE
IoP-2 | YS | ER | IoP | SPRMC | 4 | 40 | 1
IoP-3 | 27 | ESR | IoP | FSGSU | 3 | 28 | 1
IoP-3 |  | ESR | IoP | Nanocer | 7 | 38 | 1
IoP-4 | 28 | ESR | IoP | SPRMC | 4 | 19 | 1 |  |  | SPMRC | 4 | 8 |  | DONE
IoP-4 | AY | ESR | IoP | Nanocer | 6 | 26 | 1 |  |  | Nanocer | 7 | 17 |  | DONE
IoP-5 | 29 | ESR | IoP | Nanocer | 6 | 32 | 1
IoP-5 | MC | ESR | IoP | SPRMC | 1 | 22 | 1 | 12 |  | SPMRC | 1 | 8 |  | DONE
IoP-5 |  | ESR | IoP | Nanocer | 7 | 40 | 1
NC-1 | 30 | ER | Nanocer | HZG | 2 | 12 | 1 |  |  |  | 2 | 14 |  | Reported
NC-1 | PG | ER | Nanocer | HZG | 2 | 36 | 1 |  | moved to NC-4
NC-1 |  | ER | Nanocer | SPRMC | 1 | 4 | 1 | [6 empty] | DONE
NC-1 |  | ER | Nanocer | FSGSU | 6 | 42 | 1 |  |  |  |  | 26
NC-1 |  | ER | Nanocer | VU | 6 | 30 | 1 |  |  |  |  | 33
NC-1 |  | ER | Nanocer | UA | 1 | 9 | 1 | [6 empty] | DONE
NC-1 |  | ER | Nanocer | VU | 7 | 22 | 1 |  | moved to new MNG | UA | 2 | 32 | 1
NC-1 |  | ER | Nanocer | UA | 7 | 20 | 1 | [6 empty] | DONE
NC-2 | 31 | ER | Nanocer | HZG | 2 | 29 | 1 |  | moved to NC-4
NC-2 |  | ER | Nanocer | FSGSU | 1 | 8 | 1 | [6 empty] | DONE
NC-2 |  | ER | Nanocer | UA | 2 | 12 | 1 |  | moved to #30 |  |  | >M17 ? |  | Reported
NC-2 |  | ER | Nanocer | VU | 3 | 16 | 1 | [6 empty] | DONE
NC-2 |  | ER | Nanocer | IOP | 4 | 32 | 1 | 14 | to be moved to #31 M???
NC-2 |  | ER | Nanocer | HZG | 2 | 40 | 1
NC-3new |  | ESR | Nanocer | HZG |  | 29.36 |  |  |  |  | 2 | 32 | 2 | added
NC-4new |  | MNG | Nanocer | HZG | [5 empty] | VU | 7 | 32 | 1 | added
HZG-1 | 40 | ER | HZG | NC | 6 | 28 | 2
HZG-1 | VH | ER | HZG | SPMRC | 2 | 38 | 1
HZG-2 | 41 | ER | HZG | NC | 6 | 35 | 1
HZG-2 | FW | ER | HZG | SPMRC | 3 | 20 | 1 |  | Vasyl H M18 | 3 | 18 | 1 |  | reported | ... by VH
HZG-3 | 42 | ER | HZG | NC | 6 | 19 | 1
HZG-3 | 42 | ER | HZG | SPMRC | 2 | 6 | 2 |  | one M moved to Carsten M17 | 2 | 17 | 1 |  | reported
HZG-3 | MS | ER | HZG | FSGSU | 1 | 34 | 1
| CB | [7 empty] | new | ? | 17 | 1 |  | added
HZG-4 | 43 | ER | HZG | SPMRC | 5 | 14 | 1 | 11 |  | 5 | 19 | 1 |  | reported
HZG-4 | MZ | ER | HZG | FSGSU | 1 | 30 | 1
SPRMC-1 | 32 | ER | SPMRC | ILTSR | 1 | 2 | 2 |  | moved to #33, #35 | NC | 6 | 12 | 1 | Reported as not decided |  |  | moved to #33 M22
SPRMC-1 | ST | ER | SPMRC | VU | 6 | 36 | 1 |  | moved to #35 M23
SPRMC-1 | decl | ER | SPMRC | ILTSR | 7 | 44 | 1 |  | to be moved to someone
SPRMC-2 | 33 | ER | SPMRC | VU | 1 | 8 | 2 |  |  | VU | 1 | 9 | 1 | DONE
SPRMC-2 | DK | ER | SPMRC | VU | 1 | 26 | 1
SPRMC-2 | decl | ER | SPMRC | IoP | 4 | 18 | 1 |  |  |  |  | 22 23
SPRMC-2 |  | ER | SPMRC | Nanocer | 6 | 40 | 1 |  |  | NC | 6 | 22 | 1 | added was #32 |  | DONE
SPRMC-2 |  | ER | SPMRC | UA | 1 | 28 | 3 |  |  | NC | 6 | 24 | 1 | added was #39 |  | DONE
SPRMC-2 |  | ER | SPMRC | HZG | 2 | 12->13? | 1 |  |  | HZG | 2 | 11 | 1 | one-m shift not reported |  |  | DONE
SPRMC-2 |  | ER | SPMRC | HZG | 2 | 4 | 1 |  |  | ILTSR | 1 | 6 | 1 | DONE | was#32
SPRMC-2 |  | ER | SPMRC | HZG | 2 | 20 | 2 |  | 1m moved to SL #38(ESR) |  |  | 20 | 1
SPRMC-3 | 34 | ESR | SPMRC | UA | 5 | 25 | 2 |  | moved to #36
SPRMC-3 | MS | ESR | SPMRC | UA | 5 | 39 | 1
SPRMC-3 |  | ESR | SPMRC | VU | 1 | 28 | 2
SPRMC-3 |  | ESR | SPMRC | ILTSR | 1 | 35 | 1
SPRMC-3 |  | ESR | SPMRC | HZG | 2 | 4 | 2 |  |  | HZG | 2 | 11->14 | 1 | Reported | DONE
SPRMC-3 |  | ESR | SPMRC | HZG | 2 | 17 | 2 |  |  |  |  | 24-25 |  | 1m moved to #37?
SPRMC-3 |  | ESR | SPMRC | HZG | 2 | 31 | 1
SPRMC-4 | 35 | MNG | SPMRC | VU | 3 | 6 | 1 |  |  | VU | 3 | 5 | 1 |  | DONE
SPRMC-4 | OI | MNG | SPMRC | UA | 3 | 20 | 2 |  | 1m moved to #36 | UA | 3 | 16 | 1 | REPORT | DONE
SPRMC-4 | decl | MNG | SPMRC | UA | 3 | 28 | 1 |  |  | UA | 5 | 29 | 1 | added | not rep | instead of #38 M24
SPRMC-4 |  | MNG | SPMRC | ILTSR | 7 | 30 | 2 |  | to be moved M33? | ILTSR | 1 | 20 | 1 | added |  | was#37
SPRMC-4 |  | MNG | SPMRC | Nanocer | 6 | 45 | 1 |  |  | ILTSR | 1 | 6 | 1 | added | DONE | was#32
SPRMC-4 |  | MNG | SPMRC | HZG | 2 | 10 | 2 |  |  | HZG | 2 | 12 | 1 |  | DONE
SPRMC-4 |  | MNG | SPMRC | HZG | 2 | 17 | 2 |  | moved to AK & AZ(ESR) | VU | 3 | 23 21 | 1 | added | not rep | DONE
SPRMC-4 |  | MNG | SPMRC | HZG | 2 | 34 | 1 |  | to be moved M37? | VU | 6 | 23 22 | 1 | added | not rep | DONE
SPRMC-5 | 36 | ER | SPMRC | ILTSR | 1 | 6 | 1 | DONE |  | UA | 3 | 16 | 1 | added | REPORT |  | DONE
SPRMC-5 | AK | ER | SPMRC | VU | 3 | 32 | 1 |  |  | VU | 1 | 9 | 1 | added (instead of DK) |  |  | DONE
SPRMC-5 | decl | ER | SPMRC | Nanocer | 6 | 12 | 3 |  | 6 / 14,18,20 / 3 | HZG | 2 | 12 | 1 | added | DONE
[10 empty] | UA | 5 | 28 | 2 | added | not rep | instead of #34 M25-26
SPRMC-6 | 37 | ESR | SPMRC | VU | 1 | 6 | 1 |  |  | VU | 1 | 11 | 1 | VU | 1 | 12 | 1 | DONE
SPRMC-6 | AZ | ESR | SPMRC | UA | 3 | 25 | 2 |  | M25->??
SPRMC-6 | decl | ESR | SPMRC | UA | 3 | 41 | 1
SPRMC-6 |  | ESR | SPMRC | ILTSR | 1 | 8 | 1 |  | moved to ER | ILTSR | 1 | 12 | 1 | moved to OI
SPRMC-6 |  | ESR | SPMRC | HZG | 2 | 10 | 2 |  |  | HZG | 2 | 7 | 2 |  | DONE
SPRMC-6 |  | ESR | SPMRC | HZG | 2 | 31 | 2 |  |  | HZG | 1 | 14 | 2 1 | added | 1 | 20 | 1 | reported or not | DONE
SPRMC-6 |  | ESR | SPMRC | HZG | 2 | 38 | 1 |  |  | HZG | 2 | 19 | 1 | added | DONE
SPRMC-7 | 38 | ESR | SPMRC | ILTSR | 1 | 6 | 1 |  |  |  | 1 | >14=16 | 1 |  | DONE
SPRMC-7 | Py | ESR | SPMRC | VU | 3 | 32 | 1 |  |  | HZG | 2 | 12->13 | 1 | added | DONE
SPRMC-7 | SL | ESR | SPMRC | UA | 5 | 24 | 1 |  | moved to #35 M29 | HZG | 2 | 20 | 1 | added | DONE
SPRMC-8 | 39 | ESR | SPMRC | UA | 5 | 16 | 1 |  |  |  |  | 21 |  |  | not rep | DONE
SPRMC-8 | Pa | ESR | SPMRC | VU | 3 | 20 | 1 | 71 | moved to OI | [5 empty] | not rep
SPRMC-8 | DZ | ESR | SPMRC | Nanocer | 6 | 24 | 1 |  | moved to #33 M24
SECONDMENTS PLAN
Note on B34: Aleksej Zarkov
Note on B35: Anton Popov
Note on B36: (Monika Skruodiene) Jolanta Raudonienė
Note on B37: Andrius Pakalniskis
Note on B38: Zivile Stankeviciute
Note on B41: Vladimir Gaishun
Note on B56: Mikhail Maskvichou - ESR
Note on B58: Yanina Kasianok
Note on B61: S. Khakhomov changed with VS
Note on B65: V. Sidsky changed with SK
Note on C69: od 2019 ER
Note on C70: od 2019 ER
Note on J75: not working in UA from I 2020
Note on B80: Yehor Slobodianyk
Note on B84: Andrii Yaremkevych
Note on B105: Vasyl Haramus
Note on B107: Florian Wieland
Note on B110: Maria Serdechnova
Note on B113: Mikhail Zheludkevich
Note on N118: reported M8 shift to #36
Note on B127: Maxim Silibin
Note on G146: not moved to M22
Note on B154: Searhei Latushka
Note on B157: Dzmitry Zhaludkevich

## Graph
|  | 17 | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021
|  | xii | i | ii | iii | iv | v | vi | vii | viii | ix | x | xi | xii | i | ii | iii | iv | v | vi | vii | viii | ix | x | xi | xii | i | ii | iii | iv | v | vi | vii | viii | ix | x | xi | xii | i | ii | iii | iv | v | vi | vii | viii | ix | x | xi
| ID | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | NEW ID | Researcher-months
INTiBS | 1 | [48 empty] | 1 | 3 | bar: 2019 vii 48
| 2 | 4: M2; 2019 vii 29: M5; 2019 vii 42: G7 | 3 | 3
| 3 | [48 empty] | 5 | 2 | bar: 9; 2019 vii 42
| 4 | 4: M1; 2019 vii 22: M3; 2019 vii 30: G7; 2019 vii 39: G5 | 4 | 3
| 5 | [48 empty] | 6 | 2 | bar: 4; 2019 vii 30
| 6 | 2019 vii 23: M5; 2019 vii 32: M1; 2019 vii 41: G7 |  | 3
| 7 | [48 empty] | 2 | 3 | bar: 1; ix 10; xii 13; 2019 vii 27
VU | 8 | [49 empty] | 2 | bar: 2019 vii 28
| 9 | 5: M1; 2019 vii 25: G2; 2019 vii 36: G1; 2019 vii 46: Nc6 |  | 4
| 10 | [49 empty] | 3 | bar: ix 10
| 11 | 9: Nc1; 2019 vii 35: G1 |  | 3
| 12 | 8: Nc1; 2019 vii 32: Nc6 |  | 3
VU6 | bar: 2019 vii 24
VU7
VU8 | bar: 2019 iv 17
VU9 | bar: 2019 iv 17
| VU10 | 8: Nc7
FSGSU | 13 | 6: W2; 7: W2; 2019 vii 21: W2; 2019 vii 28: W2; 2019 vii 32: UA5; 2019 vii 33: VU3; 2019 vii 34: UA5; 2019 vii 37: W2; 2019 vii 44: Nc7 |  | 8
| 14 | 6: W1; x 11: VU1; 2019 vi 19: W2; 2019 vii 37: W3; 2019 vii 44: Nc6 |  | 6
| 15 | 6: W1; x 11: VU1; 2019 vii 28: Nc6; 2019 vii 30: Hzg2 |  | 5
| 16 | 2019 vii 20: Hzg2 |  | 2 |  |  |  |  | Δ =
| 17 | 2019 vii 20: Hzg2; 2019 vii 30: Hzg2; 2019 vii 32: Hzg2 |  | 3 | INTiBS | 8.9 | 9 | 19 | 0.1
| 18 | 2019 vii 21: VU3; 2019 vii 25: W1; 2019 vii 33: VU3; 2019 vii 37: W3 |  | 3 | VU | 8.13 | 8 | 15 | -0.13
| 19 | 2019 vii 20: IoP4; 2019 vii 30: Hzg2 |  | 3 | UA | 5.05 | 7 | 13 | 1.95
UA | 20 | 9: Nc3; 2019 vii 28: Nc6; 2019 vii 47: M7 |  | 2 | IOP | 4 | 5 | 12 | 1
| 21 | [49 empty] | 3 | NC | 6 | 8 | 14 | 2 | bar: 2019 vii 23; 2019 vii 29 to 2019 vii 30
| 22 | [49 empty] | 2 | HZG | 2.76 | 5 | 11 | 2.24 | bar: 2019 iv 17 to 2019 v 18
| 23 | [49 empty] | 4 | GSU | 13.6 | 16 | 30 | 2.4 | bar: 2019 vii 28; 2019 vii 30; 2019 vii 36
| 24 | 2019 vii 21: M1; 2019 vii 26: Nc6 |  | 2 | SPMRC | 30.3 | 33 | 60 | 2.7
IOP | 25 | [49 empty] | 3 |  | 78.74 | 91 | 174 | 12.26 | bar: 2019 vii 26; 2019 vii 30; 2019 vii 35
| 26 | 2019 iv 17: Nc6; 2019 vii 40: M4 |  | 2
| 27 | 2019 vii 28: G3; 2019 vii 38: Nc7 |  | 2
| 28 | 8: M1; 2019 iv 17: Nc7; 2019 vii 26: Nc6 |  | 2
| 29 | 8: M4; 2019 vii 32: Nc6; 2019 vii 40: Nc7 |  | 3
NC | 30 | 4: M1; 9: UA1; 2019 i 14: Hzg2; 2019 vii 20: UA7; 2019 vii 26: G6; 2019 vii 29: IoP4; 2019 vii 32: UA2; 2019 vii 33: VU6 |  | 8
| 31 | 8: G1; 2019 iii 16: VU3; 2019 vii 40: Hzg2
Hzg2
|  | 2019 vii 32: VU7 |  | 6
SPMRC | 32 | [49 empty] | 4 | bar: 2019 vii 44
| 33 | 6: W1; 9: VU1; xii 13: Hzg2; 2019 vii 20: Hzg2; 2019 vii 22: NC6; 2019 vii 24: NC6; 2019 vii 26: VU1; 2019 vii 27: IoP4; 2019 vii 28: UA1; 2019 vii 40: Nc6 |  | 12
| 34 | 2019 i 14: Hzg2; 2019 vii 26: Hzg2; 2019 vii 28: VU1; 2019 vii 31: Hzg2; 2019 vii 35: W1; 2019 vii 39: UA5 |  | 11
| 35 | 5: VU1; 6: W1; xi 12: Hzg2; 2019 iii 16: UA3; 2019 vii 21: VU3; 2019 vii 22: VU6; 2019 vii 26: W1; 2019 vii 28: UA3; 2019 vii 29: UA5; 2019 vii 30: W7; 2019 vii 34: Hzg2; 2019 vii 45: NC6 |  | 12
| 36 | 5: VU1; 6: W1; xi 12: Hzg2; 2019 i 14: nc6; 2019 iii 16: UA3; 2019 v 18: Nc6; 2019 vii 20: Nc6; 2019 vii 28: UA5; 2019 vii 32: VU3 |  | 5
| 37 | 7: Hzg2; xi 12: VU1; 2019 ii 15: Hzg2; 2019 vi 19: Hzg2; 2019 vii 27: Hzg2; 2019 vii 28: UA3; 2019 vii 31: Hzg2; 2019 vii 38: Hzg2; 2019 vii 41: UA3 |  | 10
| 38 | xii 13: Hzg2; 2019 iii 16: W1; 2019 vii 20: Hzg2; 2019 vii 32: VU3 |  | 3
| 39 | 2019 vii 20: UA5 |  | 3
HZG | 40 | 2019 vii 28: NC6; 2019 vii 38: M2 |  | 3
| 41 | 2019 v 18: M3; 2019 vii 35: NC6 |  | 2
| 42 | 2019 iv 17: M2; 2019 vii 26: NC6; 2019 vii 34: G1 |  | 4
| 44 | 1: Carsten - added; 2019 iv 17: M2
| 43 | [49 empty] | 2 | bar: 2019 vii 20; 2019 vii 30
|  | 2019 vii 35: duration (M) |  | 174
[5 empty] | W | ▬ | ILTSR PAS (Wroclaw) | [9 empty] | Number |  |  | ▬ | Work Package number | [12 empty] | WP1 |  | 1 | 36
[5 empty] | VU | ▬ | VU | [9 empty] | e.g. Hzg2 |  |  | ▬ | Secondment to HZG within WP2 | [12 empty] | WP2 |  | 3 | 40
[5 empty] | UA | ▬ | UA | [26 empty] | WP3 |  | 6 | 42
[5 empty] | Hzg | ▬ | HZG | [11 empty] | M1 | ▬ | „mission completed” | [12 empty] | WP4 |  | 8 | 42
[5 empty] | IoP | ▬ | IOP | [11 empty] | M2 | ▬ | „mission started" | [12 empty] | WP5 |  | 12 | 42
[5 empty] | Nc | ▬ | Nanoceramics | [11 empty] | G1 | ▬ | to be moved or updated | [12 empty] | WP6 |  | 18 | 46
[5 empty] | G | ▬ | FSGSU (Gomel) | [26 empty] | WP7 |  | 3 | 48
[5 empty] | M | ▬ | SPMRC (Minsk) | [11 empty] | M1 | ▬ | moved or modified WP | [12 empty] | WP8 |  | 1 | 48
Note on AY3: updated ID No. from PP
Note on AZ3: not updated
Note on K6: moved from M8
Note on F7: Moved from month5 finished in July
Note on X7: instead #1 M21 #4 #5 #7
Note on F8: Moved from month5; finished in Sept.
Note on Y9: instead M18
Note on L10: moved from M3 substituted (was WS) finished M25
Note on AD11: was M26
Note on G12: moved from M4
Note on AA12: instead of #10
Note on L13: new-moved from #9 M5 to M8 to M10
Note on J15: new-moved from #11 M10
Note on Z16: instead of #12
Note on S18: instead of #10
Note on S19: instead of #10
Note on J20: new-moved from #8 M9
Note on H21: moved from M8
Note on I21: moved from M9 finished in M13
Note on W21: was M19
Note on AD21: was M31, started in M26, M28 continuation
Note on AH21: moved from #18, M18 ->M20 -> ...
Note on AI21: was #16 M26
Note on AJ21: was #19 M28
Note on AM21: was M32
Note on H22: moved from M21
Note on M22: moved from M9
Note on U22: moved from #13, M20
Note on AM22: was #16 M34
Note on H23: moved from M21
Note on M23: moved from M9
Note on AD23: was #18 M30
Note on AF23: was M28
Note on V24: moved from #13, M4 to M10 to M16 moved to Moskvichov M20
Note on V25: moved from M17
Note on AF25: was #14 M28
Note on AH25: was #15 M29
Note on W26: moved from M24
Note on AA26: moved from #19, M18
Note on AI26: was #17 M26
Note on AM26: was #17 M34
Note on AF27: was #14 M29
Note on AD28: was #24 M18
Note on Y29: was M15 to M19 to M23
Note on AE29: was #23 M37
Note on S30: 2-m shift from M15
Note on AD31: was M25
Note on W32: moved from #21 M16 to M19 to M23… …to #24 M21 (Slabov)
Note on AB32: moved from M18
Note on AB33: was M19
Note on AK33: to be moved from M19
Note on S34: moved from M9 WP6 started too early
Note on J36: moved from M19 to M7 done in M8 was M4
Note on S36: moved from M9 #25
Note on J37: moved from M22 was M1
Note on F38: moved from M3
Note on K38: Moved from M8 and WP6
Note on P38: moved from M12
Note on AB38: was M42
Note on AE38: was #31 M32 to be moved to M..?
Note on AH38: was #31 M12
Note on AI38: was M30
Note on AH40: was #31 M29 & #30 M36
Note on AH41: was #30 M22
Note on AL42: was VU6 moved to #35 M23
Note on O43: moved from M12 not reported
Note on X43: moved from #32 M2
Note on Z43: moved from #39 M24
Note on AC43: moved from M18 to M22 to M23...
Note on P44: moved from M14 (new employer-Maxim) finished M20
Note on AB44: was M25
Note on H45: było VU3
Note on R45: from M20
Note on S45: was M17-18 Hzg2
Note on W45: was #39 M20
Note on X45: was #32 M36
Note on AB45: was M25 W1 instead of AZ M12
Note on AE45: was #38 M24
Note on AF45: o be moved to M33-34
Note on AJ45: to be moved to M37
Note on N46: added was M12-14 Nc6
Note on R46: added from #35 M21
Note on T46: from M12; not reported yet
Note on V46: moved from M13, not reported
Note on AD46: was #34 M25-26
Note on J47: byłoW1
Note on M47: was moved VU1
Note on N47: was moved W1
Note on P47: was Hzg moved to M20
Note on Q47: done in January
Note on U47: added
Note on V47: not reported yet
Note on AC47: #34 moved from M17 to M23 to #37 ???
Note on O48: added to M12 then moved to M13
Note on R48: was M6; Reported as a new person, >M14 Sergei L.
Note on V48: moved from #33 M21
Note on Z48: was UA5
Note on V49: was M16, DZ
Note on T51: Vasyl, moved from M20
Note on S52: moved from M6 to M13 to M17
Note on AB52: ???
Note on S53: moved from M7 #42
Note on V54: moved from M14
Note on AF54: to be moved to Carsten M17?

## graphSPMRC
|  | 17 | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021
|  | xii | i | ii | iii | iv | v | vi | vii | viii | ix | x | xi | xii | i | ii | iii | iv | v | vi | vii | viii | ix | x | xi | xii | i | ii | iii | iv | v | vi | vii | viii | ix | x | xi | xii | i | ii | iii | iv | v | vi | vii | viii | ix | x | xi
| ID | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
SPMRC | 32 | bar: 2019 vii 44
| 33 | 6: W1; 9: VU1; x 11: Hzg2; 2019 vii 20: Hzg2; 2019 vii 24: Nc6; 2019 vii 25: Nc6; 2019 vii 26: VU1; 2019 vii 28: UA1; 2019 vii 32: IoP4
| 34 | x 11: Hzg2; 2019 vii 35: W1; 2019 vii 39: UA5; 2019 vii 42: Hzg2
| 35 | 5: VU1; 6: W1; xi 12: Hzg2; 2019 iii 16: UA3; 2019 vii 23: VU6; 2019 vii 24: VU3; 2019 vii 28: UA3; 2019 vii 29: UA5; 2019 vii 32: VU1; 2019 vii 37: Hzg2; 2019 vii 45: NC6
| 36 | 5: VU1; 6: W1; xi 12: Hzg2; 2019 i 14: nc6; 2019 iii 16: UA3; 2019 v 18: Nc6; 2019 vii 20: Nc6; 2019 vii 28: UA5; 2019 vii 29: UA5; 2019 vii 32: VU3; 2019 vii 36: W7
| 37 | 7: Hzg2; x 11: VU1; 2019 ii 15: Hzg2; 2019 vi 19: Hzg2; 2019 vii 20: Hzg2; 2019 vii 25: Hzg2; 2019 vii 31: Hzg2; 2019 vii 35: UA3; 2019 vii 41: UA3
| 38 | 6: W1; xi 12: Hzg2; 2019 vii 21: Hzg2; 2019 vii 24: Hzg2; 2019 vii 30: Hzg2; 2019 vii 34: W1; 2019 vii 37: VU3
| 39 | 2019 vii 21: UA5; 2019 vii 30: UA1
All 60 PM
2017-2019 30,32 PM
2020-2021 29,68 PM
SPMRC table 28 PM
Note on V5: added
Note on S7: was M17-18 Hzg2
Note on Y7: was moved W1
Note on Z7: was moved W1
Note on N8: added was M12-48 Nc6
Note on R8: added
Note on J9: byłoW1
Note on M9: was moved W1
Note on P9: was Hzg moved to M20
Note on Q9: added
Note on U9: added
Note on V9: added
Note on AA9: added
Note on W10: added
Note on Z10: added
Note on AJ10: was UA3 M20-21 W1 instead of AZ M12
Note on W11: added